## Slide 1
1/ Present (John)
2/ Apologies (John)
3/ Minutes of last meeting (John)
4/ Proposals- (Garth)
Discussion - Name Change of committee to "Organising Group" or similar (see PowerPoint for action)
Shift from minutes to capturing actions
5/ Objective to discuss and agree - 2023 Events and Actions - Outcome - Agree event dates and owners for 2023, issue to club. (All)
6/ Review PowerPoint doc and agree action / owners for 2023. (All)
7/ AOB

## Slide 2
Present: Garth Pearson (Chair), John Miroslaw, Andrew Isherwood, Keith Jardine, Amy Ferry, Kevin Chalmers, Alan Gray, Stuart Laidlaw, Ruth Isherwood
Apologies: None
Minutes of last meeting were agreed as a true record of the meeting. Matters arising: see PowerPoint for action
It was agreed for the “committee” to be known as the "Organising Group" and that the notes of the meeting will be focused on capturing actions.
A provisional calendar of events was agreed and those with firm dates will be put in the Website calendar
The PowerPoint slides:- Weekly/Regular cycling events, Ride events, Social Events, General Actions and Other ideas to develop were discussed.
AOB - None

## Slide 3
Weekly /Regular Cycling Events | Organiser (s) | Confirmed Y/N | Added to Calendar & comms | Actions
New 12mph social group | Ruth | y | y | How to ride in a group? GCN video-Stuart Andrew – publish handbook again
Saturday 17mph Road Ride | Andrew, Stuart , Matt | Y | y | How to ride in a group? GCN video-Stuart Andrew – publish handbook again
Saturday 15mph social ride | Ewan | y | y | How to ride in a group? GCN video-Stuart Andrew – publish handbook again
Tuesday and Sunday Gravelly | Garth, Scott, Nige | y | y | Add to calandar Garth
Summer Chain Gang | Stuart | y | y | 
Summer Time Trial | Kevin | y | y | Publicity How to build engagement?
Kids Club | Scott | y | y | All in place
Bike and Blether | Colin | y | y | All in place
Winter Zwift | Keith | Y | y | All in place
Gravel crit | Garth | Y | y | Add to calandar

## Slide 4
Ride Events | Date | Organiser | Confirmed Y/N | Added to Calendar | Actions
Road Race | 29 April | Al / Scott F / Richard Allen | Y | y | Al has raised with BC – working group up and running
Tour of Tweeddale | 27th August | Chris / Garth | Y | y | Form working Group Gravel route to be included this year
Tweed-duro | 2nd April | Jo/Garth | y | y | Jo taking on supported by Garth; Keith to talk to Murray re using Glentress Hotel
Gravel meet Dumfries or Kielder | Possibly late Feb | Garth | y | y | 
Gravel meet Aviemore | 10/11 June | Jo Merritt | Y | y | Jo organising
Road/Gravel/MTB meet Lake District | July or Oct | Andrew | N | n | 
Fun Race | TBC | Matt? | N | N | Andrew to liaise with Matt
Jenny Graham ladies ride out | 6/5/23 | Ruth | y | Y | Intro Ruth to Jenny Graham Publicise
Jenny Graham all ride out | 7/5/23 | Ruth | y | Y | Intro Ruth to Jenny Graham Publicise
Grand Fondo | 29 July | Jo Merritt | Y | Y | Jo confirm with Franco costs, routes etc
Gravel TOT | 16th Sept | Chris & Garth | Y | Y | 

## Slide 5
Social Events | Date | Organiser | Confirmed Y/N | Added to Calendar | Actions
Trial Club Quiz night GT Hotel | TBC | Keith / Garth | N | Y | Anyone know good quiz master? Keith to check with Murray
Swap shop / table sale of cycling kit | 11 or 25 March | John | Y | Y | St Josephs
Larger social event summer similar to 25th | 2 September |  | y | y | Keith to check with Murray
Talks Mark Beaumont | 23/3/23 | Garth/Al | y | y | Identify general help needed. Tempus clothing display? PCC Slide show, stand in foyer, Feathers etc, flyer
Talk Jenny Graham | 6/5/23 | Garth/Al | y | Y | Identify general help needed. Tempus clothing display? PCC Slide show, stand in foyer, Feathers etc
Talk who next? | TBC | Kevin / Amy / Ruth | N | N | Maybe Christina McKenzie Ruth?, Lucy Grant, Grant Ferguson, Cameron Mason, Corran?
Cycle Law Scotland Talk – Rod Mitchell offer |  | Garth | N | N | Discussion needed if we would like this, might help ride leaders. Agreement probably not.

## Slide 6
Ref | General Actions | Comments | Actions
1 | Change Name of Committee | New name that is more inclusive and less intimidating e.g. PCC Organising Group? | All – Agreement to change to Organising Team, refer to this in all comms.
2 | Club female diversity | Build female representation and numbers, new club ride. | Ruth
3 | Club event calendar issued | Feedback from members suggesting diary of events for the year issued in January would be helpful; include insurance and be a member comments. | Calendar agreed to be published asap by Garth
4 | Sponsorship | Garth met Rod Mitchell, options discussed e.g. funding of TOT and some other individual events | Follow up January with Rod – Happy to help £2500 offered
5 | Short Course mini DH | Approached by KICC and Crank to run event with them in summer | Scott W following up
6 | Instagram / Social Media / web site | There is a club Instagram account, don’t know who moderator is. Web site has out of date content. | Stuart 1/to check if Lucy Grant owns Instagram account. Open new account if not. 2/ Speak to Jenny Badger on web site
7 | Charity Support in 2023 | Peeblesshire Paths Group? Mountain Rescue, other? Should we sponsor the path? Decision needed | Proposals for charities from all please.
8 | World Champs 2023 | Scott W has introduced Garth via email to Paul Davis 2023 World Champs Competition Manager regarding PCC presence in Event Village, we have been added to the waiting list. Confusion remains a theme. Garth needs to pick up with Kathy Gilchrist | PCC rep needed to liaise with Paul
9 | Kids Club Racing | Identify kids for XC sponsorship, discuss with parents, sponsor first races in SXC series and support with mentor at races. Feargus Pearson has volunteered as mentor, need 2 more. | Scott / Garth. Formally identify kids, discuss and put into place. Test outcome if it has longevity, next step possible Race Team Stu?

## Slide 7
Ref | General Actions | Comments | Actions
10 | Trial a Kids club Bike Maintenance session “Get you home” | Nick Tanner and Feargus Pearson have agreed to trial some bike maintenance sessions. E.g. fixing broken chain etc. | Agree dates with Nick and publicise. Garth
11 | Fun Race | Garth discussed with Bill Brown possibility of using farm to run a fun race | Discuss all, follow up with Bill Brown
12 | Review membership names / google groups / has everyone paid? | All members included on email circulation, can we automate further? | John and Andrew to check via membership. Ongoing
13 | Social event coordinator | Keep tabs on social calendar etc. | Discuss all, suggestions, nominations
14 | Social Media coordinator | Keep tabs on social media, develop club presence by publicising events, Insta, FB & Web | Stu.
15 | Tempus Cycling Club Kit | Andrew and some others trialing test kit. Kit looks okay so far, need to get a woman’s and other sample. | Andrew
16 | Identify helper pool | Pool of people who can dip in and out to run events e.g. quiz night in support of Organising group | All could each member of group try and get one volunteer?
17 | High Five Deal | Rewards programme - Discount available to club members of 40%, spend drives return to club of 10% cashback on purchases, checked small print and no issues. Recommend sign up. | Agreed to do – Garth has signed club up.
18 | Club member discount at Bspoke | Garth in discussion with Nick and Pip | Follow up Jan
19 | Club member discount at Alpine | Andrew discussed with Alpine 10% agreed | Alpine need club ID – Andrew suggests use email confirmation membership paid. Need to advertise to members

## Slide 8
Ref | General Actions | Comments | Actions
20 | Club Member Discount at Glentress |  | Keith to discuss with Murray
21 | Club Member discount at Omni |  | Andrew picking up with Sean
22 | Roll of Honour |  | Al
23 | Whiskey for Chris | Ex chair gift | Kevin
24 | Treasurer Handover | In progress | Andrew / Garth
15 | First Aid Courses | Open to members leading / organising rides | Ruth
26 | Insurance | Discuss approach further for next year | all
27 | Saddle drunk review | Poll members on experience | Kevin
28 | Add Scott W to organising group | Kids club discussions | John
29 | West Lothian Cycle Track | Connect with West Lothian Clarion so we get involved | John / Al

## Slide 9
Other Ideas to develop | Daft or Not? | Actions
Fund raising calendar for 2024? |  | 
Race Team for Adults, lead by example? |  | 
West Lothian Cycle Track |  | Al to let us know of opening date and check if we can attend.
Kids bikepacking trip? |  | 
Runner v bike with Moorfoots |  |